## Sheet1
Hutton Parish Festival Week (HPFW) Project Plan 2026 - as at 5th Jul 26
Title | Task | Responsibility and Agreements and Notes
General and Pre Events | Refresh Hutton Parish Festival Week (HPFW) Project Plan for 2026 | Confirmed by Pete Dutton
| Arrange HPFW Planning Meeting | Confirmed by Pete Dutton- booked for 30th June 26 - in HVH. In attendance - Pete D, Mark O, Claire ?, Ken Mc, Chris?, Jim S, Eric H, James O, Marg S, Mar C, Wendy W, Pat W, Sarah C, Reece ?, Jane B
| Modify HPFW flyers and arrange printing | Agreed - no HPFW flyers to be produced or distributed
| Design and print TOS, Horticultural Show and Proms event posters for Parish notice boards | Agreed - each organiser or organisation to design, print and advertise their own posters
| Advertise posters on Parish notice boards | Agreed - each organiser or organisation to design, print and advertise their own posters
| Confirm TOS Market | Confirmed by Sarah Cope and now Ken McCulloch (email address toshutton@gmail.com) who has taken over from Sarah
| Agree TOS Market Stall Holders charity recipient. | Agreed - Pancreatic Cancer Charity
| Confirm Quiz Night | Confirmed by Jane Barry
Cancelled | Confirm Horticultural Show | Originally confirmed by Terry Porter. Agreed - now cancelled
| Confirm United Benefice Songs of Praise | Confirmed by Jane Barry
| Confirm Hutton Dabaso Twinning Committee - Big Bash | Confirmed by Hutton Dabaso Twinning Committee
| Confirm Classic Car Show | Confirmed by Jim Spence
Done in mid August | Distribute HPFW flyers | Agreed - no HPFW flyers to be produced or distributed
| Arrange signage | Volunteers
| Advertise events in Hutton Parish News - copy date - now delayed until week ending 10 Jul | Agreed - each organiser or organisation to advertise their event in the HPN. Tony Pass has agreed to assist where possible.
| Inform Weston Mercury | Tony Pass (HPN Editor)
| Inform Mendip Times | Tony Pass (HPN Editor)
| Arrange Bar | Agreed - Hutton Dabaso Twinning Cttee to arrange for the whole week
| Arrange Event License | Agreed - Hutton Dabaso Twinning Cttee to arrange for the whole week
| Security - Sleep-overs | Agreed - Hutton Dabaso Twinning Cttee to arrange for the whole week
| HPN, PC Website and Facebook notice for call for volunteers to help with show | Hutton PC - Pete Dutton and PC Clerk
| First Aid for events | First Aid Kit and Accident Book. See PC Events Health and Safety Risk Assessment
| PC Events Health and Safety Risk Assessment | Pete Dutton - see HPFW 26 Health and Safety Risk Assessment
| PC Fire Risk Assement | Pete Dutton -see HPFW 26 Fire Risk Assessment
| Arrange Scout Hut Toilet cleaning and stock maintenance | Pete Dutton - see HPFW 26 - Scout Hut Cleaning Roster
| Restock Scout Hut Cleaning Materials and Toilet Rolls | Pete Dutton - to be done before the HPFW events
| Arrange TOS parking volunteers & PC radios & high viz jackets | Pete Dutton - see TOS Car Parking Roster
| Order Large Marquee and associated items - dance floor required | Confirmed by Hutton PC. Deposit paid by Hutton PC. Balance to be paid by Hutton PC,
| Restock Reuseable plastic beer cups if required | Agreed - not required - Hutton Dabaso Twinning Cttee to use their reuseable plastic beer cups.
| PAT test all PC electrics | Hutton PC via Pete Dutton & PC Clerk. Hutton Dabaso Twinning to assist if required.
| Trim hedge for electrics | Hutton PC via Pete Dutton & PC Clerk
| Service Fire Extinguishers in the Scout Hut | Hutton PC via Pete Dutton & PC Clerk
| Wifi Connection at Scout Hut | Volunteers
| Arrange floodlights for outside toilets | Volunteers
| Order Waste Bins from NSC - extra to be ordered because Horticultural Bar (cans & bottles only) & Hutton Dabaso Big Bash | Hutton PC via Pete Dutton & PC Clerk
Taste of Somerset (TOS) Market - Day Event - Wednesday 2nd Sep 26 | Task | Responsibility and Notes
| L2 Food Hygiene Certificate Letter to be sent to Market Stallholders selling food | Ken McCulloch (signed letter obtained from PC Clerk)
| Invite Market Stall Holders | Ken McCulloch
Done on Tues 1 Sep 26 | Erect small PC marquee | Volunteers
Done on Tues 1 Sep 26 | Collect electrics and other items from Village Hall and Terry's | Volunteers
Done on Tues 1 Sep 26 | Install electrics in main and small marquee | Volunteers
Done on Tues 1 Sep 26 | Install Fire Extinguishers from Scout Hut | Volunteers
Done on Tues 1 Sep 26 | Install and set up Bar | Agreed - Hutton Dabaso Twinning Cttee for the whole week
Done on Tues 1 Sep 26 | Install and set up PA system | Eric Holdaway & volunteers
Done on Tues 1 Sep 26 | Install and set up signage | Volunteers
Done on Tues 1 Sep 26 | Erect main marquee | Contractor - Archer's
Done on Tues 1 Sep 26 | Set out furniture in Main Marquee and Small Marquee for TOS Market | Ken McCulloch & Volunteers
Done on Tues 1 Sep 26 | Collect and set up PC Scout Hut Staging (for TOS musicans) in main marquee | Ken McCulloch & Volunteers
Done on Tues 1 Sep 26 | Walkways to be sited correctly | Contractor - Archer's
Done on Tues 1 Sep 26 | Set up red walkway barriers from PC Scout Hut Container | Volunteers
Done on Tues 1 Sep 26 | Set up Car Parking parking rows and signs from PC Scout Hut Container | Volunteers
Done on Tues 1 Sep 26 | Clean Scout Hut Toilets | Volunteers - see HPFW 26 Scout Hut Cleaning Roster
Done on Tues 1 Sep 26 | Security - Tues Sleep-over | Hutton Dabaso Twinning Cttee to arrange for the whole week
| Manage Car Parking, PC Radios and High Viz Jackets | Pete Dutton & volunteers - see HPFW 26 TOS Car Parking Roster
| Manage TOS Market event and Stall Holders | Ken McCulloch
| Collect Market Stall Holders charity contributions | Ken McCulloch
Done on a date TBD after the event | Distribute Market Stall Holders charity contributions to the chosen Charity | Ken McCulloch
| Manage Bar | Hutton Dabaso Twinning Cttee for the whole week
| Set up and manage Classic Car Show event | Jim Spence
| Clean Scout Hut Toilets | Volunteers - see HPFW 26 Scout Hut Cleaning Roster
| Tidy up after event including Scout Hut | Ken McColloch & volunteers
| Set up Quiz Night tables & chairs | Jane Barry & St Mary's Church
| Security - Wed Sleep-over | Hutton Dabaso Twinning Cttee to arrange for the whole week
| Secure Scout Hut and St Mary's Field | Volunteers
Quiz Night - Evening Event - Thursday - 3rd Sep 26 | Task | Responsibility and Notes
| Set up and manage Quiz Night event | Jane Barry & St Mary's Church
| Manage Horticultural Society Bar | Agreed - to be arranged by Hutton Dabaso Twinning Cttee for the whole week
| Clean Scout Hut Toilets | Volunteers - see HPFW 26 Scout Hut Cleaning Roster
| Tidy up after event including Scout Hut | Jane Barry & St Mary's Church
| Security - Thur Sleep-over | Hutton Dabaso Twinning Cttee to arrange for the whole week
| Secure Scout Hut and St Mary's Field | Jane Barry & St Mary's Church
Horticultural Society Flower Show - Day Event - Cancelled | All Task Cancelled | Responsibility and Notes
Cancelled | Set up tables and show benches | Agreed - now cancelled
Cancelled | Set up table clothes and mark out spaces, with numbers | Agreed - now cancelled
Cancelled | Pick up Alcoves and other items from Village Hall | Agreed - now cancelled
Cancelled | Set up Alcoves etc | Agreed - now cancelled
Cancelled | Set up Horticultural Society Flower Shows control desks and laptop and printer | Agreed - now cancelled
Cancelled | Set up and put up all School entries including pictures and handwriting | Agreed - now cancelled
Cancelled | Restock Horticultural Society Bar if required | Agreed - now cancelled
Cancelled | Physically receive and manage show entries on Friday evening in the Marquee until 10pm | Agreed - now cancelled
Cancelled | Give out cards for each entry | Agreed - now cancelled
Cancelled | Clean Scout Hut Toilets | Agreed - now cancelled
Cancelled | Secure Scout Hut and St Mary's Field | Agreed - now cancelled
Cancelled | Arrange schedule | Agreed - now cancelled
Cancelled | Send out schedule | Agreed - now cancelled
Cancelled | Invite Show entries | Agreed - now cancelled
Cancelled | Receive show entries and enter into the computer | Agreed - now cancelled
Cancelled | Arrange School children's sections | Agreed - now cancelled
Cancelled | Arrange and allocate Judges | Agreed - now cancelled
Cancelled | Arrange and allocate Stewards | Agreed - now cancelled
Cancelled | Arrange Prize Giver | Agreed - now cancelled
Cancelled | Arrange food for judges and stewards | Agreed - now cancelled
Cancelled | Arrange gift for prize giver (flowers) | Agreed - now cancelled
Cancelled | Return and collect and correlate all cups and trophies for prize giving | Agreed - now cancelled
Cancelled | Order RHS medals Banksian | Agreed - now cancelled
Cancelled | Order RHS medals for Dahlia | Agreed - now cancelled
Cancelled | Order RHS medals for Chrysanthemum | Agreed - now cancelled
Cancelled | Order RHS medals for Veg | Agreed - now cancelled
Cancelled | Modify software schedule | Agreed - now cancelled
Cancelled | Print schedules | Agreed - now cancelled
Cancelled | Distribute schedules to past participants | Agreed - now cancelled
Cancelled | Put out Horticultural show banners | Agreed - now cancelled
Cancelled | Order table coverings | Agreed - now cancelled
Cancelled | Arrange cake covers | Agreed - now cancelled
Cancelled | Arrange plastic flower holders | Agreed - now cancelled
Cancelled | Arrange table covers | Agreed - now cancelled
Cancelled | Arrange Hose, long special fitting from Terry Porter | Agreed - now cancelled
Cancelled | Arrange watering can is available for exhibits | Agreed - now cancelled
Cancelled | Tea and coffee (scout hut) | Agreed - now cancelled
Cancelled | Childrens sports invite organiser | Agreed - now cancelled
Cancelled | Arrange Food Vendors | Agreed - now cancelled
Cancelled | Physically receive and manage show entries on Sat morning in the Marquee from 7am until judging starts. | Agreed - now cancelled
Cancelled | Prepare and print Judges paperwork for all classes | Agreed - now cancelled
Cancelled | Manage the judging | Agreed - now cancelled
Cancelled | Enter judging results on the computer | Agreed - now cancelled
Cancelled | Print prize cards | Agreed - now cancelled
Cancelled | Distribute prize cards | Agreed - now cancelled
Cancelled | Manage Horticultural Society Flower Show event | Agreed - now cancelled
Cancelled | Manage Horticultural Society Bar | Agreed - now cancelled
Cancelled | Prepare cups and trophies for prize giving | Agreed - now cancelled
Cancelled | Arrange, manage and present prizes - cups and trophies | Agreed - now cancelled
Cancelled | Arrange, manage and give out prize money | Agreed - now cancelled
Cancelled | Arrange and manage auction of goods after show | Agreed - now cancelled
Cancelled | Arrange and manage childrens classes on a separate sheet | Agreed - now cancelled
Cancelled | Break down and remove all Horticultural Society Flower Show items and equipment including show benches from the Main Marquee | Agreed - now cancelled
Cancelled | Roll up and store school show entries | Agreed - now cancelled
Cancelled | Clean Scout Hut Toilets | Agreed - now cancelled
Cancelled | Spray Chrysanthemums take from Mike Higgins for Sunday morning United Benefice Songs of Praise - moorning event | Agreed - now cancelled
Cancelled | Tidy up after event including Scout Hut | Agreed - now cancelled
Cancelled | Handover Marquees and Scout Hut to Hutton Dabaso Twinning Committee | Agreed - now cancelled
Main Marquee Free - Friday 4th Sep 26 | Task | Responsibility and Notes
Main Marquee Free | Available for hire | Hutton PC & PC Clerk
| Security - Fri Sleep-over | Hutton Dabaso Twinning Cttee to arrange for the whole week
Hutton Dabaso Twinning Committee - Big Bash - Evening Event - Saturday 5th Sep 26 | Task | Responsibility and Notes
700 (Seven Hundred) attendees Max including staff. | Arrange Event Notice (TEN) and Public Liability Insurance | Hutton Dabaso Twinning Committee
Set up - 4pm onwards | Set up Hutton Dabaso Twinning Committee - Big Bash | Hutton Dabaso Twinning Committee. As much as possible to be set up in advance on Tuesday 1 Sep 26 and Thursday 3rd Sep 26
Start - 7pm | Set up Hutton Dabaso Twinning Bar & License. | Hutton Dabaso Twinning Committee
Last Orders - 11:15pm | Security | Hutton Dabaso Twinning Committee
Finish and vacated by 11:45pm | Set up additional toilets | Hutton Dabaso Twinning Committee
No overnight camping or parking | Arrange and manage bands | Hutton Dabaso Twinning Committee
| Dance Floor required? Yes | Ordered and fitted with Main Marquee - Pete Dutton
| Arrange additional power and electrics if required | Hutton Dabaso Twinning Committee
| PC Scout Hut Staging and separate Dabaso Twinning Cttee staging to be used. | Hutton Dabaso Twinning Committee.
| Hutton Parish Council - St Mary's Field (Including Scout Hut) Conditions of use | Pete Dutton - Signed by Hutton Dabaso Twinning Committee
| Arrange and manage Scout Hut as changing rooms | Hutton Dabaso Twinning Committee
| Arrange and manage car parking | Hutton Dabaso Twinning Committee
| Arrange and manage food vendors- to be cooked outside only - away from the Marquees | Hutton Dabaso Twinning Committee
| Big Bash piece for the HPFW Flyer | Agreed - no HPFW flyers to be produced or distributed
| Big Bash piece for the Hutton Parish News - copy date - now delayed until week ending 10 Jul | Hutton Dabaso Twinning Committee - to be passed to the Editor of the Hutton Parish News
| Install Bar in small Marquee on Tuesday 1st Sep or Thursday 3rd Sep | Hutton Dabaso Twinning Committee
| First Aid | Hutton Dabaso Twinning Committee - see Health and Safety Risk Assessment
| Manage Hutton Dabaso Twinning Committee - Big Bash event | Hutton Dabaso Twinning Committee
| Health and Safety Risk Assessment | Hutton Dabaso Twinning Committee
| Clean Scout Hut Toilets | Hutton Dabaso Twinning Committee
| Fire Risk Assement | Hutton Dabaso Twinning Committee
| Remove all Hutton Dabaso Twinning Committee - Big Bash items and equipment including from the Main and PC Marquee | Hutton Dabaso Twinning Committee
| Tidy up after event including Scout Hut | Hutton Dabaso Twinning Committee
| Security - Sat Sleep-over | Hutton Dabaso Twinning Cttee to arrange for the whole week
| Secure Scout Hut and St Mary's Field | Hutton Dabaso Twinning Committee
United Benefice Songs of Praise - Morning Event - Sunday 6th Sep 26 | Task | Responsibility and Notes
| Set up United Benefice Songs of Praise event | Jane Barry & St Mary's Church
| Manage United Benefice Songs of Praise event | Jane Barry & St Mary's Church
| Clean Scout Hut Toilets | Volunteers - see HPFW 26 Scout Hut Cleaning Roster
| Tidy up after event including Scout Hut | Jane Barry & St Mary's Church
| Secure Scout Hut and St Mary's Field | Jane Barry & St Mary's Church
Hutton Proms Concert - Evening Event - Sunday 6th Sep 26 | Task | Responsibility and Notes
Done on Sun 6th Sep during the afternoon | Set up tables | Jane Barry & St Mary's Church & volunteers
Done on Sun 6th Sep during the afternoon | Set up flowers for proms tables | Jane Barry & St Mary's Church & volunteers
Done on Sun 6th Sep during the afternoon | Set up raffle | Jane Barry & St Mary's Church & volunteers
Done on Sun 6th Sep during the afternoon | Secure Scout Hut and St Mary's Field in the afternoon after set up. | Jane Barry & St Mary's Church
| Book band and soloists for Proms night - Weston Brass | Jane Barry & St Mary's Church & Eric Holdaway
| Send advert to Show Secretary to add to schedule | Jane Barry & St Mary's Church
| Arrange and manage printing of tickets | Jane Barry & St Mary's Church
| Arrange and manage selling of tickets | Jane Barry & St Mary's Church
| Agree and arrange table quantity | Jane Barry & St Mary's Church
| Arrange Raffle | Jane Barry & St Mary's Church
| Arange food for band | Jane Barry & St Mary's Church
| Manage Bar | Agreed - to be arranged by Hutton Dabaso Twinning Cttee for the whole week
| Manage the Proms Concert event | Jane Barry & St Mary's Church
| Arrange and manage Scout Hut as changing rooms | Jane Barry & St Mary's Church
| Arrange and print Programmes | Jane Barry & St Mary's Church & Eric Holdaway
| Clean Scout Hut Toilets | Volunteers - see HPFW 26 Scout Hut Cleaning Roster
| Tidy up after event including Scout Hut | Jane Barry & St Mary's Church
| Security - Sun Sleep-over | Hutton Dabaso Twinning Cttee to arrange for the whole week
| Secure Scout Hut and St Mary's Field | Jane Barry & St Mary's Church
Take Down, Re-Store and Tidy Up - Morning - Monday 7th Sep 26 | Task | Responsibility and Notes
| Take down, re-store and get equipment ready for pick up | Volunteers
| Move Small PC Marquee back to Scout Hut Container and electrical equipment to PC Store in Hutton Village Hall | Volunteers
| Removal of Bar | Hutton Dabaso Twinning Committee
| Removal of Hutton Dabaso Twinning Cttee Marquee and any other equipment | Hutton Dabaso Twinning Committee
| Contractor takes down and takes away large Marquee | Contractor - Archer's
| Final tidy up of St Mary's site & Scout Hut | Volunteers
| Clean Scout Hut Toilets | Volunteers - see HPFW 26 Scout Hut Cleaning Roster
| Secure Scout Hut and St Mary's Field | Volunteers
| Arrange pick up of bins and waste by NSC | Hutton PC via Pete Dutton & PC Clerk